## Blad1
As a … | , I want to ... | so that I can… | Priority (MoSCoW) | Sprint | Status
Carer | Access the dashboard from any device with internet. | Always update my client's activities at any time. | Must | 2 | To be started
Carer | Login with my personal account | Make sure nobody else will create or edit activities for my client. | Must | 2 | To be started
Carer | Program a person's tasks for the day, week or month | Manage my client's activities for any selected time. | Must | 2 | To be started
Carer | Modify a person's tasks at any time | Update mistakes or new schedules for my client. | Must | 2 | To be started
Carer | Configure the order of activities and change the duration for one or more persons | Give the client more comfort when executing activities if needed. | Must | 2 | To be started
Carer | Configure who receives the "panic" button notifications. | Personaly notify my self or relatives of the client. | Must | 2 | To be started
Carer | Configure an action when a person activates the "panic" button. (call, text or e-mail) | Help the client if something goes wrong or if the client does not know what to do. | Must | 2 | To be started
Carer's client | View all the activities that the carer has programmed | See what activities I have to do in a certain period. | Must | 2 | To be started
Carer's client | To click a panic button | Call for help from my client if needed. | Must | 2 | To be started
Carer's client | Automatically view all steps of the activity when clicking the notification | t be distracted by anything else on the app and can execute the activity fast. | Must | 2 | To be started
Carer's client | Get a overview of all scheduled tasks when finishing a task | See what activities in the future I have to do. | Must | 2 | To be started
Carer's client | See voice, text and images for each step in the activity | Easily follow the steps even when blind or deaf. | Must | 2 | To be started
Carer's client | See how much time a step in a activity should take | See how much time I have left for the activity. | Must | 2 | To be started
Carer's client | Repeat the instruction on each step | Repeat the instructions if not clear enough. | Must | 2 | To be started
Carer's client | Get a notification when its time for a activity | Be notified when there is a new activity to execute. | Must | 2 | To be started
Carer's client | Only have the app active when its time for a new activity | I can't be distracted or anoyed by the app when not in use. | Must | 2 | To be started
|  |  | Must | 0 - Setup | To be started
|  |  | Should | 1 - Design | Work in progress
|  |  | Could | 2 - Development | Done
|  |  | Would | 3 - Testing & hardening